## Project Planner
Project Planner
Gantt-style timeline: mark weeks with "██" (active) or leave blank. % Complete is editable.
Activity | Assigned To | Start | Days | % Complete | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Discovery & brief | Alex | 2026-08-31 16:00 | 5 | 100% | bar: W1 to W2
Research | Jordan | 2026-09-02 16:00 | 8 | 80% | bar: W2 to W3
Wireframes | Sam | 2026-09-09 16:00 | 7 | 50% | bar: W3 to W4
Design system | Sam | 2026-09-14 16:00 | 10 | 30% | bar: W4 to W6
Build MVP | Alex | 2026-09-21 16:00 | 14 | 15% | bar: W5 to W7
QA & polish | Jordan | 2026-10-05 16:00 | 7 | 0% | bar: W7 to W8
Launch | Alex | 2026-10-12 16:00 | 3 | 0% | bar: W8
Overall % complete |  | 39.3%